## Month 1 Program Status
Total Project Scope
Project | Total # Robots | Total # Shelves | Total Budget | Acceptable Defect Rate (Robots, Shelves)
Project 1 | 1000 | 9135 | 30817 | 1%
Project 2 | 27 | 340 | 4025 | 1%
Project 3 | 573 | 2240 | 18959 | 1%
Project 4 | 8737 | 20931 | 60788 | 1%
Project 5 | 9000 | 55401 | 70990 | 1%
Project 6 | 473 | 2490 | 16668 | 1%
Project 7 | 10 | 72 | 2000 | 1%
Project 8 | 713 | 2639 | 21230 | 1%
Project 9 | 10987 | 100010 | 54030 | 1%
End of Month 1 Summary
Project | # Robots Installed - 1st month plan | # Robots Installed - Actual | # Defective Robots | # Shelves Installed - 1st month Plan | # Shelves Installed - Actual | # Defective Shelves | Budget - Actual
Project 1 | 399 | 595 | 5 | 3654 | 3948 | 72 | 6163.4
Project 2 | 21 | 7 | 3 | 21 | 2 | 0 | 805
Project 3 | 224 | 511 | 27 | 448 | 448 | 12 | 3791.8
Project 4 | 6986 | 3493 | 8 | 4186 | 4000 | 24 | 12157.6
Project 5 | 8099 | 7196 | 100 | 55398 | 52876 | 682 | 28396
Project 6 | 91 | 42 | 22 | 994 | 1500 | 27 | 3333.6
Project 7 | 0 | 4 | 0 | 28 | 72 | 3 | 600
Project 8 | 350 | 497 | 17 | 791 | 800 | 17 | 6369
Project 9 | 7686 | 2191 | 40 | 50001 | 20000 | 156 | 16209